## Group Sprint Info
Group #: | 12 | Sprint #: | 2
Client/App Name: | WorkSafeBC/MSI360 | Sprint Objective: | Complete translations and report generation
Group Member 1: | Cole | Outcome/User stories to be completed in this sprint
Group Member 2: | Jonah | Number | Title
Group Member 3: | Kyle | 1 | User wants questions and answers to be in their spoken language
Group Member 4: | Nicholas | 2 | User wants their results in a shareable PDF report
Group Member 5: | Abdullah

## Test Cases
Outcome/User stories | Test Case ID | Title | Objective | Preconditions | Expected Result | Actual Result | Status | Comments | Execution Date | Executed By
User wants their results in a shareable PDF report | MT-08 | PDF report | Complete an assessment and select download PDF | User has completed the survey and is on the final result page | PDF downloads and includes the score overview and answered questions | The PDF downloaded properly and included all the required info | Pass |  | 2026-05-12 | Cole
User wants questions and answers to be in their spoken language | MT-17 | Spanish task parity | Enter equivalent English and Spanish lifting task descriptions. | Gemini API key is configured, user is on language selection page | Both runs show the same core lifting/repetition follow-up questions; very small tag variance is acceptable. | Both languages returns the same tag list and question pre-answers | Pass |  | 2026-05-13 | Jonah
User wants questions and answers to be in their spoken language | MT-18 | French task parity | Enter equivalent English and French desk/computer task descriptions. | Gemini API key is configured, user is on language selection page | Both runs show the same core seated/screen/repetition follow-up questions; very small tag variance is acceptable. | Both languages returns the same tag list and question pre-answers | Pass |  | 2026-05-13 | Jonah
User wants their results in a shareable PDF report | MT-19 | PDF visual layout | Open the downloaded PDF from low-risk and high-risk sample assessments | PDF renderer is fully functional | Exactly same layout as the design on Figma board | Exactly same layout as the design on Figma board | Pass |  | 2026-05-14 | Kyle
User wants questions and answers to be in their spoken language | MT-17 | Spanish task parity | Enter equivalent English and Spanish lifting task descriptions. | Gemini API key is configured, user is on language selection page | Both runs show the same core lifting/repetition follow-up questions; very small tag variance is acceptable. | Both languages returns the same tag list and question pre-answers | Pass |  | 2026-05-14 | Nicholas
User wants their results in a shareable PDF report | MT-19 | PDF visual layout | Open the downloaded PDF from low-risk and high-risk sample assessments | PDF renderer is fully functional | Exactly same layout as the design on Figma board | Exactly same layout as the design on Figma board | Pass |  | 2026-05-14 | Nicholas
User wants their results in a shareable PDF report | MT-20 | AI-generated report analysis | With Gemini configured, answer Q1-Q4, continue through the assessment, wait briefly on the report-ready screen, then download the PDF. | PDF renderer is fully functional | The overview page shows an "AI-generated analysis" block beside "Job-specific note"; it includes the fixed Q1-Q4 AI disclaimer and source links to Institute for Work & Health and WorkSafeBC OHS Regulation Part 4. | AI generated paragraph as expected | Pass |  | 2026-05-14 | Kyle
User wants their results in a shareable PDF report | MT-22 | Responder/tenure AI context | With Gemini configured, run one scenario as Worker with less than a year in role and another as Supervisor/Manager with the same task. Compare the AI-generated analysis paragraphs. | PDF renderer is fully functional | Worker output treats the answer as directly task-relevant; non-worker output recommends review with a worker, and short-tenure output references elevated new-worker injury risk without changing category scores. | Correct responder context added to PDF | Pass |  | 2026-05-14 | Kyle
User wants their results in a shareable PDF report | MT-21 | PDF report downloads successfully | Verify that the user can download the completed assessment as a PDF report | The user has completed the assessment and reached the results page | The PDF downloads successfully and can be opened | The PDF downloaded successfully and opened correctly. | Pass |  | 2026-05-15 | Abdullah
User wants their results in a shareable PDF report | MT-23 | PDF includes assessment answers | Verify that the downloaded PDF includes the user’s assessment questions and answers | The user has completed the assessment and generated the PDF report | The PDF includes the user’s answered questions in the report | The PDF included the answered questions correctly | Pass |  | 2026-05-15 | Abdullah

## Bug Reports
Bug ID | related Test Case ID | Description | Severity | Reported By | Reported On | Status | Fixed By | Fixed On | Comments
#111 | MT-17 | Regression issue causing Gemini API to send incorrect tags for English Prompt | Medium | Jonah | 2026-05-14 | Fixed/Closed | Jonah | 2026-05-14 | Fixed. Gemini API call seemed to have been over analyzing English prompts. Adjusted prompt to return to old logic when translation isn't necessary.

## Sheet1 (hidden)
New/Open:
In Progress
Fixed/Closed